## User Story
Issue Type | Issue ID | Summary | Discription
Epic 1 | UN-7 | Forgot Password | To validate the forgot password funtion
Story 1 | UN-13 | Forgot Password (With Subscription) | Objective : Any registered user, who has forgotten their password, can reset/change it Acceptance 1 : Valid registered email is entered and a link is sent to said email. Acceptance 2 : New password must be at least 8 characters long. Note: To reset password, the user must be subscribed.

## Test Scenarios
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_UN_008 | ForgotPassword (with subscription) | To check whether when we select the forgot password to link it is directing to forgot the password link page. | UI | 1 | Click on the 'Forgot Password' button
TS_UN_009 |  | Check system behaviour when valid email is entered to the forgot password column. | Functional Testing | 1 | Enter a valid registered email id in the specified field as input
TS_UN_010 |  | To check whether the link was sent to the mail to which the user has provided | Functional Testing | 1 | Open the registered email id to check if a link is sent to reset password
TS_UN_011 |  | To check whether the link can be used once once | Functional Testing | 1 | After resetting the password, click on link again to check if it works
TS_UN_012 |  | Check whether new password set is also meeting requireents. | Functional Testing | 2 | 1. Enter a valid password, meeting all the requirements. 2. Enter a password that does not meet all the requirements.
TS_UN_013 |  | To check whether the user now logs in with the new password and it is working | Functional Testing | 4 | 1. Login with valid email and newly set password. 2. Login with valid email and a wrong password. 3. Login with invalid email and the newly set password. 4. Login with invalid email and password.

## Test Case
TestCase ID | Test Scenario | Test Condition | Preconditions | Priority | Test Steps | Test Data | Expected Result | Actual Result | Status Iteration | Actual Result Iteration 2 | Status Iteration 2 | Comments | Req. References
UN-T18 | Verify Forgot your password button | To verify the Forgot page | url https://www.universalclass.com/ login.html should be working | Normal | "1. Open the https://www.universalclass.com /login.html on url" |  | Should display the forgot passwod page to enter the email, reset password button | opens the forgot passsword page
UN-T19 | Verify user is subscribed | To verify subscribed email | url https://www.universalclass.com/ myclasses/forgotpassword.html should work | Normal | 1. Open the https://www.universalclass.com /myclasses/forgotpassword on url 2.Enter the subscribed email | Email : papsru1997@gmail.com | Should display message Password reset link has been sent to the registered email | Displays message Password reset link has been sent to the registered email
UN-T20 | Verify the link sent to reset password | To verify the link sent to email to reset password | url https://www.gmail.com should work | Normal | 1. Open https://www.gmail.com 2. Open the email sent from universalclass. 3. Click on the link provided. | Email : papsru1997@gmail.com Password : sru**** | Should open reset password page | Opens reset password page
UN-T21 | Verify that the new password is at least 8 characters long | To verify the new password meets the password requirements | Unique link for reset password must open | Normal | 1. Enter new password which is 8 characters long 2. Reenter the new password 3. Click on 'Reset' button | New password : sruthi@12 Re-enter password : sruthi@12 | Should display confirmation message of password reset | Displays confirmation message of password reset
UN-T22 | Verify user is able to sign in with new password | To verify sign in with new password | url https://www.universalclass.com/ login.html should be working | Normal | 1. Enter subscribed email id 2. Enter newly set password | Email : papsru1997@gmail.com Password : sruthi@12 | Should show the homepage after login | Shows the homepage after login
UN-T23 | Verify the unique link is only usable once | To verify the unique link only works once | url https://www.gmail.com should work | Normal | 1. Click again on the link sent by universalclass after resetting the password |  | Should display error message | Displays error message

## Test Summary
Test summary report for Sprint 1 (27-Nov to 02-Dec)
S. No | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 1
2 | Created TestCases | 6
3 | No of tests Executed in Sprint 1, Iteration 1 | 6 | 1 | 0
4 | Defects Reported | 0
5 | Number of Sprints Executed | 1
Any Challenges
Any Best Practices

## Agile Report
Agile Report
1 | Burndown Chart
2 | Burnup chart
3 | Sprint Report
4 | Cumulative Flow
Diagram