## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.universalclass.com/
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Universal class is an online learning website. It provides high quality, online courses to help you learn the skills needed to achieve your goals. Courses on website are not just tutorials; they are real. They include lessons, exams, assignments, discussion boards and actual assessments of your progress to help you master the learning outcomes. In scope Functionality: 1)Sign in 1. Once you've opened the Universal class website, select 'Sign In' in the header of web page to be the member of the course. the 'Sign In' tab directs the user to the 'Sign In' page where the user needs to enter the credentials viz. the registered email and its corresponding password. 2.If you are a new user you can directly sign up by providing email and password in sign in page. 2)Forgot Password 1.In case you forget your password, one link: ‘Forgot your password?’ is provided below the sign in button. Once you click on the link, link redirects user to forgot password page. 2. In forgot password window, there is a textbox to enter your email id and one button to reset your password. On click of the button, password link will be sent on the entered email id to ensure security. 3)Search courses 1. A textbox in the body of web page is present to search for the interested courses. User can type the course name to be searched and click on the search icon. 2. When user enters course to be searched and click on the serch icon,user gets result related to the searched course Out of Scope Functionality: 1. Course Catalog 2. My Classes account Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Story
Issue Type | Issue Id | Summary | Description
Epic 1 | UN-6 | Sign In
Story 2 | UN-9 | Sign In (without subscription) | Objective : As a unsubscribed user you can sign in by subscribing to a plan of your choice so that you can subscribe for the unlimited course available on webpage Acceptance 1 : For any new user who want to sign up, selecting a plan for subscription is mandatory inorder to proceed further Acceptance 2 : User cannot use same email id for signing up for new account which is already associated with another username, if signing up with same email id should display message"The email address -- abcd@gmail.com is already associated with another Username on our service. Please use the 'Forgot Your Password' feature to reset your password." Acceptance 3 : User can proceed further with sign up step only by entering first name, last name, valid email id, password and selecting the checkbox for Terms of Service and Privacy Policy Acceptance 4 : For signing up with invalid email id and password should display message"Please correct the following:Your password must be at least 8 characters.Enter a valid email address (name@domain.com)." Acceptance 5 : Email id should be verified by clicking on verification link or by entering the verification code provided in email id, mentioned while creating the account NOTE : for signup dependency is "choosing a plan" for subscription , which you can see by clicking on "subscribe" option available on webpage https://www.universalclass.com/

## Test Scenario
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details | Test Case ID
TS_SignUp_01 | UN-9 | Verify UI page for Sign Up | UI | 3 | 1. Check for subscribe option in home page 2. Check for the different plans available for subscription 3. Check for the sign Up page with first name, last name, email and password textbox, checkbox for selecting terms of service and sign up button | UN-T12
TS_SignUp_02 |  | Verify Sign Up page with valid input | Functional | 3 | 1. Check for the Email Verification Page 2. User should be sign in successfully once the email is verified | UN-T13
TS_SignUp_03 |  | Verify Sign Up page with invalid input | Functional | 6 | Check the error message for all the invalid input | UN-T14

## Test Cases
Test Case ID | Test Scenario | Preconditions | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (To be updated only if test cases failed in iteration1) | Status Iteration 2 (To be updated only if test cases failed in iteration1) | Comments | Req: Reference
UN-T12 | Verify UI page for Sign Up | Url https://www.universalclass.com/ should be working | Verify that menu icon should have "Subscribe" option | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. |  | Pop-up menu should have Subscribe option | Pop-up menu show Subscribe option | Pass
|  |  | Verify that on the click of Subscribe option different plan for subscription is shown | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option |  | Should display different plan for subscription | Different plan for subscription is shown | Pass
|  |  | Verify that after selecting the plan we are redirected to Sign Up page and all the textbox fields, checkbox and button is displayed | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice |  | Sign Up page is displayed which has First Name, Last Name, Email, and Password textbox, Checkbox for accepting Terms of Service and Privacy Policy and Sign Up button | Sign Up page is displayed which has First Name, Last Name, Email, and Password textbox, Checkbox for accepting Terms of Service and Privacy Policy and Sign Up button | Pass
UN-T13 | Verify Sign Up page with valid input | Url https://www.universalclass.com/ should be working | Verify that user is redirected to "Verify Your Email" page after clicking on Sign Up button | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button | First Name : Smita Last Name : Mhatre Email : smitamhatre538@gmail.com Password : smita123 | Should redirect to "Verify Your Email" page | Redirecting to "Verify Your Email" page | Pass
|  |  | Verify that user is redirected to "Verify Your Email" page after saving the changes made by user by clicking on edit profile | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button 8. Click on edit profile (if entered email id is incorrect) 9. Enter correct email id 10. Click on Save changes | First Name : Smita Last Name : Mhatre Email : smitamhatre538@gmail.com Password : smita123 | Should redirect to "Verify Your Email" page | Not redirecting to "Verify Your Email" page instead of it user is already even though email is not verified | Fail
|  |  | Veryify that user have been successfully sign in after the verification process of email | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button 8. Click on Send Verification Email button 9. Click on the verification link or can enter verification code 10. Click on continue | First Name : Smita Last Name : Mhatre Email : smitamhatre538@gmail.com Password : smita123 | User should be Sign In successfully | User have been Sign In Successfully | Pass
UN-T14 | Verify Sign Up page with invalid input | Url https://www.universalclass.com/ should be working | Verify that the error message is displayed when all the required fields are kept blank and after that we click on Sign Up button | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Click on Sign Up button | all required fields are blank | Should display message Please correct the following: Your password must be at least 8 characters. Enter your first name. Enter your last name. Enter an email address. You must agree to the Terms of Service (read and check box) | Display message: Please correct the following: Your password must be at least 8 characters. Enter your first name. Enter your last name. Enter an email address. You must agree to the Terms of Service (read and check box) | Pass
|  |  | Verify that the error message is displayed when we entered all the required fields but don't select the checkbox for accepting Terms of Service and click on Sign Up button | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Click on Sign Up button (Don't select the checkbox for accepting Terms of Service and Privacy Policy) | First Name : Smita Last Name : Mhatre Email : smita@gmail.com Password : smita123 | Should display message Please correct the following: You must agree to the Terms of Service (read and check box) | Display message: Please correct the following: You must agree to the Terms of Service (read and check box) | Pass
|  |  | Verify that the error message is displayed when we try to input invalid characters in First Name and Last Name | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button (For first name and last name try to input special characters and digits) | First Name : 12@sm Last Name : sm@12 Email : smita@gmail.com Password : smita123 | Should display message Please correct the following: First name and last name should only contain characters | Instead of showing error message for inputing invalid characters in first name and last name, it is been proceed with further steps | Fail
|  |  | Verify that the error message is displayed when we try to input invalid email id | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button (Enter invalid email id) | First Name : Smita Last Name : Mhatre Email : smita_gmail.com Password : smita123 | Should display message Please correct the following: Enter a valid email address (name@domain.com). | Display message: Please correct the following: Enter a valid email address (name@domain.com). | Pass
|  |  | Verify that the error message is displayed when we try to input invalid password | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button (Enter invalid password) | First Name : Smita Last Name : Mhatre Email : smita@gmail.com Password : smita | Should display message Please correct the following: Your password must be at least 8 characters. | Display message: Please correct the following: Your password must be at least 8 characters. | Pass
|  |  | Verify that the error message is displayed when we enter the email id which is already used by another user | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button (Enter email id which is already associated with other username) | First Name : Smita Last Name : Mhatre Email : smita@gmail.com Password : smita | Should display message Please correct the following: The email address -- smita@gmail.com is already associated with another Username on our service. Please use the 'Forgot Your Password' feature to reset your password. | Display message: Please correct the following: The email address -- smita@gmail.com is already associated with another Username on our service. Please use the 'Forgot Your Password' feature to reset your password. | Pass

## Defect Report
Defect ID | Defect Summary | Reportedby | Date | AssignedTo | Severity | Priority | Status | Module | BuildVersion | Reproducable | Reprosteps | Expected | Actual
UN-27 | Not Redirecting to "Verify Your Email Page" | akankshay77@gmail.com | 2020-12-02 |  | Medium | Medium | To Do | Sign In (without subscription) | Sprint 1 | Yes | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button 8. Click on edit profile (if entered email id is incorrect) 9. Enter correct email id 10. Click on Save changes | After entering the coreect email id and saving the changes, the page should redirect to "Verify Your Email" page | Once we have corrected the email id and save the changes, we are not redirecting to any page instead the user is sign in even though email verification process is not done
UN-28 | Invalid characters in First Name and Last Name | akankshay77@gmail.com | 2020-12-02 |  | Medium | Medium | To Do | Sign In (without subscription) | Sprint 1 | Yes | 1. Go to url https://www.universalclass.com/ 2. On the right side of navigation bar there is a menu icon click it. 3. Click on Subscribe Option 4. Choose the plan as per your choice 5. Enter all the required input 6. Select the checkbox for accepting Terms of Service and Privacy Policy 7. Click on Sign Up button (For first name and last name try to input special characters and digits) | Should display error message Please correct the following: First name and last name should only contain characters | Accepting special characters and digits for First Name and Last Name input value

## Test Summary
Test summary report for Sprint 1 (27-Nov to 02-Dec)
S. No | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 1
2 | Created TestCases | 3
3 | No of tests Executed in Sprint 1, Iteration 1 | 12 | 10 | 2
4 | Defects Reported | 2
5 | Number of Sprints Executed | 1
Any Challenges
Any Best Practices

## Agile Report
Agile Report
1 | Burndown Chart
2 | Burnup chart
3 | Sprint Report
4 | Cumulative Flow
Diagram