## User Story
Issue Type | Issue ID | Summary | Discription
Epic 1 | UN-20 | Home Page | To validate the home page
Story 1 | UN-20 | Home Page | Objective : As a user, I should be able to access the home page when I open the URL https://www.universalclass.com/, so that I can access all the services provided by the website. Acceptance 1 : Home page opens Note: Any user can access this page

## Test Scenario
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_Home_001 | Home Page | Verify if https://www.universalclass.com opens | UI | 1 | Open the URL in the browser
TS_Home_002 |  | Verify if the words on the page are accurate | Functional Testing | 2 | 1. Type a valid search option 2. Type an invalid search word
TS_Home_003 |  | Verify if page is responsive | UI | 1 | Resize the windows and check if all the content is visible

## Test Case
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 | Status Iteration 2 | Comments | Req: Reference
TS_Home_001 | Verify if https://www.universalclass.com opens | URL https://www.universalclass.com must be working | To check if URL is working | Open URL https://www.universalclass.com |  | Page should open | Page opens
TS_Home_002 | Verify if the words on the page are accurate | URL https://www.universalclass.com must be working | To verify words on the home page | ​​​​​Open the URL 'https://www.universalclass.com' and check the words/phrases displayed there. | ​Search word : 'Selenium' | The words should be accurate | The course does not exist
TS_Home_003 | Verify if page is responsive | URL https://www.universalclass.com must be working | To verify that the page is responsive and so the content fits itself as the window is resized. | ​1. Open the URL https://www.universalclass.com 2. Resize the window once page opens. |  | All the page's content should be visible | Page is not responsive

## Defect Reporting
Defect Id | Summary | Reported by | Date | Assigned to | Severity | Priority | Status | Module | BuildVer | Reprodecable | ReproSteps | Expected Result | Actual Result
UN-18 | The home page has the words that say 'Learn Anything' which is misleading to the user as the site does not provide courses on all topics imaginable. | chandrakantha.sruthi-pappu@capgemini.com | 2020-12-02 | dev@email.com | Normal | Medium | ToDo | Home Page | Sprint 1 | Yes | 1. Go to https://www.universalclass.com 2. Change the words and remove the ones that aren't accurate | Words should not be misleading | Words are misleading
UN-19 | The webpage, when resized, loses some of the content on it. The buttons for Browse Courses and My Classes is not visible when the size of the window is reduced. | chandrakantha.sruthi-pappu@capgemini.com | 2020-12-02 | dev@email.com | Normal | Medium | ToDo | Home Page | Sprint 1 | Yes | 1. Go to https://www.universalclass.com 2. Change the code and make the page more responsive | Page should be responsive and if window is resized, all the content should be visible | Page is not responsive. Two buttons are not visibe when page is resized.

## Test Summary
Test summary report for Sprint 1 (27-Nov to 02-Dec)
S. No | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 1
2 | Created TestCases | 3
3 | No of tests Executed in Sprint 1, Iteration 1 | 3 | 1 | 2
4 | Defects Reported | 2
5 | Number of Sprints Executed | 1
Any Challenges
Any Best Practices

## Agile Report
Agile Report
1 | Burndown Chart
2 | Burnup chart
3 | Sprint Report
4 | Cumulative Flow
Diagram