## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.universalclass.com/ | Page displayS a textbox for user to enter the Coursename and a search icon beside it.
Sprint Day | Sprint Activity |  | Overview and scope of functionality | Search bar and search icon are present at the center of the webpage
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template |  | Project Overview: Universal class is an online learning website. It provides high quality, online courses to help you learn the skills needed to achieve your goals. Courses on website are not just tutorials; they are real. They include lessons, exams, assignments, discussion boards and actual assessments of your progress to help you master the learning outcomes. In scope Functionality: 1)Sign in 1. Once you've opened the Universal class website, select 'Sign In' in the header of web page to be the member of the course. the 'Sign In' tab directs the user to the 'Sign In' page where the user needs to enter the credentials viz. the registered email and its corresponding password. 2.If you are a new user you can directly sign up by providing email and password in sign in page. 2)Forgot Password 1.In case you forget your password, one link: ‘Forgot your password?’ is provided below the sign in button. Once you click on the link, link redirects user to forgot password page. 2. In forgot password window, there is a textbox to enter your email id and one button to reset your password. On click of the button, password link will be sent on the entered email id to ensure security. 3)Search courses 1. A textbox in the body of web page is present to search for the interested courses. User can type the course name to be searched and click on the search icon. 2. When user enters course to be searched and click on the serch icon,user gets result related to the searched course Out of Scope Functionality: 1. Course Catalog 2. My Classes account Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing | Placeholder 'I want to learn…'is present with the search bar and it disappears when user starts typing. | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.universalclass.com/
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design |  |  | Page suggests all related courses for accounting as per entered keyword. | Overview and scope of functionality
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution |  |  | Page displays 'No records matched your search criteria.Try these course suggestions...' | Project Overview: Universal class is an online learning website. It provides high quality, online courses to help you learn the skills needed to achieve your goals. Courses on website are not just tutorials; they are real. They include lessons, exams, assignments, discussion boards and actual assessments of your progress to help you master the learning outcomes. In scope Functionality: 1)Sign in 1. Once you've opened the Universal class website, select 'Sign In' in the header of web page to be the member of the course. the 'Sign In' tab directs the user to the 'Sign In' page where the user needs to enter the credentials viz. the registered email and its corresponding password. 2.If you are a new user you can directly sign up by providing email and password in sign in page. 2)Forgot Password 1.In case you forget your password, one link: ‘Forgot your password?’ is provided below the sign in button. Once you click on the link, link redirects user to forgot password page. 2. In forgot password window, there is a textbox to enter your email id and one button to reset your password. On click of the button, password link will be sent on the entered email id to ensure security. 3)Search courses 1. A textbox in the body of web page is present to search for the interested courses. User can type the course name to be searched and click on the search icon. 2. When user enters course to be searched and click on the serch icon,user gets result related to the searched course Out of Scope Functionality: 1. Course Catalog 2. My Classes account Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git |  |  | Page gets redirected to new webpage that has particular course details
Sprint Day 5 | Sprint Evaluation |  |  | User Previous History is not displayed below search bar
User is able to search from result page itself.

## User Story
Issue Type | Issue ID | Summary | Description
Epic 3 | UN_8 | Search Course | To validate the search course functionality
Story | UN_10 | Search Courses 1 | Objective : As a User, I should be able to search courses in the search bar. Acceptance 1: A search bar should be present which should accepts inputs entered by User. Search bar and Search Icon should be in center of the webpage also a Placeholder should be available in search bar. Acceptance 2: As a User, I should be able to search for interested courses and click on search icon or press enter for the search results. Acceptance 3: Search results should appear below where all the related courses as per user’s input should be available. Suggestions of any course should be redirect to new webpage. Acceptance 4: If no results available for user’s input, Below message should be displayed on the screen: “No records matched your search criteria. Try these course suggestions…” Acceptance 5: Previous search history should be present. Acceptance 6: User should be able to search again from result page.

## Test Scenario
Requirement ID | Test Scenario ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details | Test Case ID
UN-10 | TS_SearchCourse1_01 | Verify Webpage having search bar and search icon. | UI | 3 | 1.To verify search bar and search icon option | UN_T9
[5 empty] | 2.To verify search bar and search icon location | UN-25
[5 empty] | 3. Placeholder text should be present | UN-26
| TS_SearchCourse1_02 | Verify result when course is available | Functionality | 1 | Verify result when course is available | UN-10
| TS_SearchCourse1_03 | Verify result when course is not available | Functionality | 1 | Verify result when course is not available | UN-11
| TS_SearchCourse1_04 | Verify suggestions are redirecting and course content is available or not | Functionality | 1 | Verify suggestions are redirecting properly to new webpage | UN-27
| TS_SearchCourse1_05 | Verifysearch bar history | Functionality | 1 | Verify previous inputs are present below the search bar | UN-28
| TS_SearchCourse1_06 | Check whether user can search from result page | Functionality | 1 | Verify to search again from result page | UN-29

## Test Cases
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
UN_T9 | Verify Webpage having search bar and search icon. | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in | To verify the search bar and search icon option on the webpage of Universal Class | Open URL <https://www.universalclass.com/> |  | Page should display a textbox for user to enter the Coursename and a search icon beside it. | Page displayS a textbox for user to enter the Coursename and a search icon beside it. | Pass
UN-25 |  | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in | To verify search bar and search icon location on webpage of Universal Class | Open URL <https://www.universalclass.com/> |  | Search bar and search icon should be present in the center of the webpage | Search bar and search icon are present at the center of the webpage | Pass
UN-26 |  | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in | To verify placeholder text present on search bar | Open URL <https://www.universalclass.com/> |  | Placeholder 'I want to learn…'should be present with the search bar and it should disappear when user starts typing. | Placeholder 'I want to learn…'is present with the search bar and it disappears when user starts typing. | Pass |  |  |  |  | To verify the search bar and search icon option on the webpage of Universal Class
UN-10 | Verify result when course is available | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in | Verify whether search results for course is available | 1.Open <https://www.universalclass.com/> URL 2. Enter Course Name in the search bar 3.Click on search icon/press enter | Names of Available Courses Example : Accounting | Page should suggests all related courses for accounting as per entered keyword. | Page suggests all related courses for accounting as per entered keyword. | Pass |  |  |  |  | To verify search bar and search icon location on webpage of Universal Class
UN-11 | Verify result when course is not available | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in 3. Interested course should be entered | Verify search result when course is not available | 1.Open the <https://www.universalclass.com/> URL 2. Enter Course Name in the search bar 3.Click on search icon/press enter | Course Name not available Example: Java | Page should display 'No records matched your search criteria.Try these course suggestions...' | Page displays 'No records matched your search criteria.Try these course suggestions...' | Pass |  |  |  |  | To verify placeholder text present on search bar
UN-27 | Verify suggestions are redirecting and course content is available or not | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in 3. Interested course should be entered | To verify suggestions are redirecting properly to new webpage | 1.Open the <https://www.universalclass.com/> URL 2. Enter Course Name in the search bar .Example: Accounting' 3.Click on search icon/press enter | Accounting | Page should be redirected to new webpage that should be having particular course details | Page gets redirected to new webpage that has particular course details | Pass |  |  |  |  | Verify whether search results for course is available
UN-28 | Verify search bar history | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in 3. Search bar should be available | To verify previous inputs are present below the search bar | 1. Open URL <https://www.universalclass.com/> 2. Enter inputs in search bar | Example: javascript | User Previous History should be displayed below search bar | User Previous History is not displayed below search bar | Fail |  |  |  |  | Verify search result when course is not available
UN-29 | Verify whether user can search from result page | 1. The url < https://www.universalclass.com/ > should be working 2. The user should not be signed in 3. Search bar should be available | To verify to search again from result page | 1. Open URL <https://www.universalclass.com/> 2. Enter input 1 in search bar 3. Press Enter/Search icon 4. delete input 1. 5. Enter input 2 and press enter/search icon | Input 1: Javascript Input 2: Accounting | User should be able to search from result page itself | User is able to search from result page itself. | Pass |  |  |  |  | To verify suggestions are redirecting properly to new webpage
To verify previous inputs are present below the search bar
To verify to search again from result page

## Defect Reporting
Defect Id. | Summary | ReportedBy | Date | Assigned To | Severity | Priority | Status | Module name | BuildVer | Reprodecable | ReproStepts | Expected | Actual
UN_22 | When user enters any new inputs in the search bar field, previous search history should be visible below search bar for user's convenience.Here, search history is not available after user enters his inputs. | sayali.manohar-patil@capgemini.com | 2020-12-02 |  | Medium | Medium | To Do | Search Courses 1 | Sprint 1 | Yes | 1. Open URL <https://www.universalclass.com/> 2. Enter inputs in search bar | User Previous History should be displayed below search bar | Previous search history not available.

## Test Summary
Test summary report for Sprint 1 (27-Nov to 02-Dec)
S. No | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 1
2 | Created TestCases | 8
3 | No of tests Executed in Sprint 1, Iteration 1 | 8 | 7 | 1
4 | Defects Reported | 1
5 | Number of Sprints Executed | 1
Any Challenges
Any Best Practices

## Agile Report
Agile Report
1 | Burndown Chart
2 | Burnup chart
3 | Sprint Report
4 | Cumulative Flow
Diagram